## Sheet1
Order | Role | Step | Require for Store only | Require for brand/franchise/store | Manual or Automation | Input parameters | query string
1 | CAM | CAM engages with Customer on RR — @ 50% confidence, fills out Corp Acct Onboarding Form | ? | ? | Manual
2 | Customer Success | Sales process results in Customer Agreeing to RR | ? | ? | Manual
3 | Customer | Customer provides required data: POS, Labor, Sales Forecast Data | yes | yes | Manual
4 | CAM | CAM (/CS?) works with FSS Sales Admin to set-up account in ERP — contract, sku + $s | ? | ? | Manual
5 | Customer Success | CS works with customer / CAM to identify role / permissions for customer (occurs in the CBF) | yes | yes | Manual
6 | Customer Success | CS works with CDM Ops & EGIC to setup customer in CDM NON-PROD by filling out the CBF Set up form a. Data lands in CDM ~48 hours after setup in ERP | ? | ? | Manual
6 | CDM Support | Set-up demo users a. Use Mailinator to set up demo users b. domain: @team980431.testinator.com | yes | yes | Manual
6 | CDM Support | Setup customer's users in CDM | yes | yes | Manual
7 | Customer Success | Verify initial CDM Setup complete (~3 day completion time) for NON-PROD: a. Access to sites/accts via CDM b. Demo users + permissions c. Rush Ready pipeline updated | yes | yes | Manual
8 | Customer Success | CS (or EGIC dependent on volume) completes CDM Data Readiness via [CBF] for NON-PROD (https://ecolab.sharepoint.com/sites/CDMOps2/SitePages/Requesting-a-Customer-Builder-File-(CBF)--Key-Information-and-Guidelines.aspx) | ? | ? | Manual
9 | CDM Support | CDM to enable customer roles in NON-PROD: a. envision: the user will sync to E3D b. kos?: the user has access to the dashboard for a specific set of sites. | yes | yes | Manual
10 | Engineer | Verify CDM setup, including: a. Brand, Franchise, and Site b. Users c. Locations d. Are users aligned with correct locations? e. Are demo users aligned with the correct locations? | yes | yes | Manual
11 | Engineer | Verify that E3D dev instance has a Context Point for the brand, franchise, and site | yes | yes | https://e3d-contextservice-webapi-q.azurewebsites.net/AliasService/api/v1/GetContextPoint Can proceed without waiting for step 10 but need to handle when this step failed | identifier=CKE¦¦SDC¦1100083 | { "contextPointId": 3899976, "contextPointName": "CARL'S JR #1100083", "identifiers": [ "ContextPointID¦¦3899976", "CKE¦¦SDC¦1100083" ] }
11 | Engineer | Create the aliases in E3D dev (ex. "CKE¦¦SDC¦1100083") | yes | yes | https://e3d-contextservice-webapi-q.azurewebsites.net/AliasService/api/v1/UpsertContextPointAlias Requires previous step to be completed successful first. | Leave alias id blank. { "aliasID": null, "contextPointId": 3822552, "alias": "CKE¦¦SDC¦1100083" } ] (from Peter) The only thing we ever use alias for is determining the site context point ID for a file from a customer. Those files are always site-level | 0
12 | Customer Success | Get daypart (breakfast, lunch, etc.) definitions from the customer... a. For each, get the name the customer wants to use (casing, spelling, terminology, etc.). b. For each get the start time and end time. c. Which dayparts are significant? Significant dayparts have metrics calculated for them, are included in the daily rollup, and they appear in the UI. | probably not | yes | Manual
12 | Customer Success | Get destination (drive-thru, dine-in, etc.) definitions from the customer... a. For each, get the name the customer wants to use (casing, spelling, terminology, etc.). b. Which destinations should show in the UI? | probably not | yes | Manual
12 | Customer Success | Ask the customer for the following: a. ingest.forecasted_sales_snapshots_interval (in seconds) b. ds.start_time_for_daily_aar (always per-site, HH:MM, time in 24-hour UTC) c. api.min_date (YYYY-MM-DD) d. api.kpi__sos__threshold__weekly_baseline (number) e. api.kpi__splh__threshold__weekly_baseline (number) | yes | yes | Manual
13 | Engineer | Apply dayparts to the brand, franchise, or site as appropriate in Config API for dev. Dayparts are a JSON payload with the following specs: a. The payload should be an array of objects. b. Each object has the E3D-defined "id" (type id as string) for the daypart (ex. Breakfast is 11). c. Each object has the customer-defined "name" (string) for the daypart. d. Each object has the customer-defined "start" (time as "24:00") for the daypart. e. Each object has the customer-defined "end" (time as "24:00") for the daypart. f. Each object has the customer-defined "is_significant" (true/false) for the daypart. g. Ensure that no start and end times overlap. h. ex. [{ "id": "11", "name": "Breakfast", "start": "8:00", "end": "10:59", "is_significant": true }] | probably not | yes | Config API Requires Step 12 to be completed first. brand - PUT {{url}}/brands/4182473 site: PUT {{url}}/brands/4182473/accounts/246155785/sites/3899976 For databricks team, they care about dayparts and ds.start_time_for_daily_aar .
13 | Engineer | Apply dayparts as Spans in E3D using UpsertSpanTimeConfiguration and UpsertSpanType. | probably not | yes | https://e3d-spanservice-webapi-q.azurewebsites.net/SpanService/SpanTimeConfig/api/v1/UpsertSpanTimeConfiguration Requires Step 12 to be completed first. | [ { "SpanTypeId": 0, "SiteId": 0, "StartTime": "string", "DurationInSeconds": 0, "StartOn": "2025-07-24", "ExpiryOn": "2025-07-24" } ]
13 | Engineer | Apply destinations to the brand, franchise, or site as appropriate in Config API for dev. Destinations (also known as channels) are a JSON payload with the following specs: a. The payload should be an array of objects. b. Each object has the E3D-defined "id" (type id as string) for the destination (ex. Drive-In is 1). c. Each object has the customer-defined "name" (string) for the destination. d. Each object has the customer-defined "orderIndex" (integer) that determines its sort order (lower is first). e. Each object has the customer-defined "show_in_ui" (true/false) that determines whether the destination shows in the UI. f. ex. [{ "id": "1", "name": "Dine In", "orderIndex": "2", "show_in_ui": true }] | probably not | yes | Config API Requires Step 12 to be completed first.
13 | Engineer | Apply configurations to the brand, franchise, or site as appropriate in Config API, including: a. ingest.forecasted_sales_snapshots_interval (in seconds) b. ds.start_time_for_daily_aar (always per-site, HH:MM, time in 24-hour UTC) c. api.min_date (YYYY-MM-DD) d. api.kpi__sos__threshold__weekly_baseline (number) e. api.kpi__splh__threshold__weekly_baseline (number) | yes | yes | Config API Requires Step 12 to be completed first.
14 | Engineer | Build maps for the user's data such as channel_map and span_type_map | probably not | yes | Manual
15 | Engineer | Apply destinations to the brand, franchise, or site as appropriate in Config API for dev. a. channel_map_id b. span_type_map_id c. sales_filename_pattern d. labor_filename_pattern e. order_filename_pattern | probably not | yes | Config API Requires Step 12 to be completed first.
16 | Engineer | Ingest 30 days (or 90 days if a new brand) worth of data leading up to launch date (dev) | yes | yes | Manually drop files in the customer blob container?
17 | Data Scientist | Determine slow items for a new brand or incorporate this new data into the existing brand: a. Use notebook to find slow items b. Or build a custom notebook for analysis Define the following parameters in Config API: a. max_slow_items b. min_orders_for_slow_items c. min_sos_threshold_for_slow_items d. max_sos_threshold_for_slow_items e. max_orders_for_slow_items f. max_order_count_percentile_for_slow_items | No Model is trained at brand level. | yes | Manual (Zach's notes) Those configs will be set at the brand level since we train models by brand. When we get a new brand we will need to train a new model with configuration parameters that are likely different than those for CKE. Training a new model for a brand will be manually kicked off, but we have a workflow that will run through the steps to do so. Setting those configs will take some DS evaluation
17 | Data Scientist | Determine slow customizations for a new brand or incorporate this new data into the existing brand: a. Use notebook to find customized items b. Or build a custom notebook for analysis Define the following parameters in Config API: a. max_slow_customizations b. min_orders_for_slow_customizations c. min_sos_threshold_for_slow_customizations d. max_sos_threshold_for_slow_customizations e. max_orders_for_slow_customizations f. max_order_count_percentile_for_slow_customizations | No Model is trained at brand level. | yes | Manual
17 | Data Scientist | Evaluate ML Model and Data for a new brand or incorporate this new data into the existing brand: a. Confirm production data availability and accuracy b. For existing brand, evaluate new stores against existing model (retrain model if needed) c. For new brands, run ML Training pipeline on 30 days worth of data | No Model is trained at brand level. | yes | Manual
17 | Engineer | Grant customer access to SFTP dropzone | probably not | yes | Manual
18 | Customer | Customer to set up automated drop of files into SFTP dropzone | maybe | yes | Manual
18 | Engineer | Implement preprocessor and formatter | probably not | maybe | Manaul Need to be done before step 16 (modify preproccessor, formatter) and 17 (for data scientist) can be done?
19 | Engineer | Deploy preprocessor and formatter to DEV | probably not | maybe | Manaul Need to be done before step 16 (modify preproccessor, formatter) and 17 (for data scientist) can be done?
20 | Data Scientist | Confirm relevant data is available in Databricks ADLS (DEV) | yes | yes | Manual Requires Step 18 and 19 to be completed first.
21 | Engineer | Ensure an end-to-end test is successful in DEV, including: a. Preprocessor b. Formatter c. ETL d. Daily AAR e. Visibility in Web | yes | yes | Manual Related to step 16 (drop 30 files) or just 1 day files?
22 | Engineer | Deploy preprocessor and formatter to STAGE | probably not | maybe | Manual
23 | Data Scientist | Retrain these models in STAGE, including: a. Explainer model b. Slow Items c. Slow Customizations | depends on above | yes | Manual
23 | Customer Success | CS works with CDM Ops & EGIC to setup customer in CDM PROD by filling out the CBF Set up form a. Data lands in CDM ~48 hours after setup in ERP | yes | yes | Manual
24 | Customer Success | Verify initial CDM Setup complete (~3 day completion time) for PROD: a. Access to sites/accts via CDM b. Demo users + permissions c. Rush Ready pipeline updated | yes | yes | Manual
25 | Customer Success | CS (or EGIC dependent on volume) completes CDM Data Readiness via [CBF] for PROD (https://ecolab.sharepoint.com/sites/CDMOps2/SitePages/Requesting-a-Customer-Builder-File-(CBF)--Key-Information-and-Guidelines.aspx) | ? | ? | Manual
26 | CDM Support | CDM to enable customer roles in PROD: a. envision: the user will sync to E3D b. kos?: the user has access to the dashboard for a specific set of sites. | yes | yes | Manual
26 | Engineer | Create the aliases in E3D STAGE (ex. "CKE¦¦SDC¦1100083") | yes | yes
27 | Engineer | Apply all relevant configurations from Config API in DEV to STAGE | yes | yes
28 | Engineer | Ensure an end-to-end test is successful in STAGE, including: a. Preprocessor b. Formatter c. ETL d. Daily AAR e. Visibility in Web | yes | yes | Manual
29 | Data Scientist | Retrain these models in PROD, including: a. Explainer model b. Slow Items c. Slow Customizations | depends on above | yes | Manual
29 | Engineer | Create the aliases in E3D PROD (ex. "CKE¦¦SDC¦1100083") | yes | yes
29 | Engineer | Apply all relevant configurations from Config API in DEV to PROD | yes | yes
30 | Engineer | Ensure an end-to-end test is successful in PROD, including: a. Preprocessor b. Formatter c. ETL d. Daily AAR e. Visibility in Web | yes | yes | Manual

## Sheet2
Brand: 4182473
Account/Franchise: 246155785
Context Point ID: 3899976
Context Point Name: CARL'S JR #1100083
Alias Name: CKE¦¦SDC¦1100083

## Sheet3
[
{
"brand": "_global_",
"scope": "ingest",
"key": "order_servicebus_batch_size",
"value": "25"
},
{
"brand": "_global_",
"scope": "ingest",
"key": "labor_servicebus_batch_size",
"value": "25"
},
{
"brand": "_global_",
"scope": "ingest",
"key": "sales_servicebus_batch_size",
"value": "25"
},
{
"brand": "_global_",
"scope": "x",
"key": "dayparts",
"value": "[ { \"id\": \"11\", \"name\": \"Breakfast\", \"start\": \"06:00\", \"end\": \"10:59\", \"is_significant\": true }, { \"id\": \"12\", \"name\": \"Lunch\", \"start\": \"11:00\", \"end\": \"13:59\", \"is_significant\": true }, { \"id\": \"13\", \"name\": \"Afternoon\", \"start\": \"14:00\", \"end\": \"16:59\", \"is_significant\": true }, { \"id\": \"14\", \"name\": \"Dinner\", \"start\": \"17:00\", \"end\": \"19:59\", \"is_significant\": true }, { \"id\": \"15\", \"name\": \"Late Night\", \"start\": \"20:00\", \"end\": \"23:59\", \"is_significant\": true }, { \"id\": \"16\", \"name\": \"Graveyard\", \"start\": \"0:00\", \"end\": \"5:59\", \"is_significant\": false }, { \"id\": \"17\", \"name\": \"All Day\", \"start\": \"0:00\", \"end\": \"23:59\", \"is_significant\": true } ]"
},
{
"brand": "_global_",
"scope": "x",
"key": "destinations",
"value": "[ { \"id\": \"1\", \"name\": \"Dine In\", \"orderIndex\": \"2\", \"show_in_ui\": true }, { \"id\": \"2\", \"name\": \"Carry Out\", \"orderIndex\": \"3\", \"show_in_ui\": true }, { \"id\": \"3\", \"name\": \"Drive Thru\", \"orderIndex\": \"1\", \"show_in_ui\": true }, { \"id\": \"4\", \"name\": \"Delivery\", \"orderIndex\": \"4\", \"show_in_ui\": false }, { \"id\": \"5\", \"name\": \"Online FC\", \"orderIndex\": \"5\", \"show_in_ui\": false } ]"
},
{
"brand": "_global_",
"scope": "ds",
"key": "max_slow_items",
"value": "13"
},
{
"brand": "_global_",
"scope": "ds",
"key": "min_orders_for_slow_items",
"value": "100"
},
{
"brand": "_global_",
"scope": "ds",
"key": "min_sos_threshold_for_slow_items",
"value": "10"
},
{
"brand": "_global_",
"scope": "ds",
"key": "max_sos_threshold_for_slow_items",
"value": "900"
},
{
"brand": "_global_",
"scope": "ds",
"key": "max_orders_for_slow_items",
"value": "15"
},
{
"brand": "_global_",
"scope": "ds",
"key": "max_order_count_percentile_for_slow_items",
"value": "0.9"
},
{
"brand": "_global_",
"scope": "ds",
"key": "max_slow_customizations",
"value": "13"
},
{
"brand": "_global_",
"scope": "ds",
"key": "min_orders_for_slow_customizations",
"value": "100"
},
{
"brand": "_global_",
"scope": "ds",
"key": "min_sos_threshold_for_slow_customizations",
"value": "10"
},
{
"brand": "_global_",
"scope": "ds",
"key": "max_sos_threshold_for_slow_customizations",
"value": "900"
},
{
"brand": "_global_",
"scope": "ds",
"key": "max_orders_for_slow_customizations",
"value": "15"
},
{
"brand": "_global_",
"scope": "ds",
"key": "max_order_count_percentile_for_slow_customizations",
"value": "0.9"
},
{
"brand": "_global_",
"scope": "ds",
"key": "max_sos_deviation_for_cascade_effect",
"value": "2"
},
{
"brand": "_global_",
"scope": "ds",
"key": "sos_model_version",
"value": "4.3"
},
{
"brand": "_global_",
"scope": "ds",
"key": "splh_model_version",
"value": "4.3"
},
{
"brand": "_global_",
"scope": "ds",
"key": "min_score_for_good_bad_news",
"value": "0.2"
},
{
"brand": "_global_",
"scope": "ds",
"key": "sos_anomaly_threshold",
"value": "1"
},
{
"brand": "_global_",
"scope": "ds",
"key": "sos_anomaly_explanation_threshold",
"value": "0.2"
},
{
"brand": "_global_",
"scope": "ds",
"key": "splh_anomaly_threshold",
"value": "1"
},
{
"brand": "_global_",
"scope": "ds",
"key": "splh_anomaly_explanation_threshold",
"value": "0.2"
},
{
"brand": "_global_",
"scope": "ds",
"key": "max_insights_recs",
"value": "3"
},
{
"brand": "_global_",
"scope": "ds",
"key": "sample_window_size",
"value": "90"
},
{
"brand": "_global_",
"scope": "ui",
"key": "enable_calendar_picker",
"value": "true"
},
{
"brand": "_global_",
"scope": "ui",
"key": "enable_forward_looking",
"value": "true"
},
{
"brand": "_global_",
"scope": "ui",
"key": "enable_positive_drivers",
"value": "true"
},
{
"brand": "_global_",
"scope": "ui",
"key": "enable_sos",
"value": "true"
},
{
"brand": "_global_",
"scope": "ui",
"key": "enable_sos_gauge",
"value": "true"
},
{
"brand": "_global_",
"scope": "ui",
"key": "enable_sos_weekly",
"value": "true"
},
{
"brand": "_global_",
"scope": "ui",
"key": "enable_sos_weekly_by_channel",
"value": "true"
},
{
"brand": "_global_",
"scope": "ui",
"key": "enable_sos_weekly_by_day",
"value": "true"
},
{
"brand": "_global_",
"scope": "ui",
"key": "enable_sos_weekly_themes",
"value": "true"
},
{
"brand": "_global_",
"scope": "ui",
"key": "enable_splh",
"value": "true"
},
{
"brand": "_global_",
"scope": "ui",
"key": "enable_splh_gauge",
"value": "true"
},
{
"brand": "_global_",
"scope": "ui",
"key": "enable_splh_weekly",
"value": "true"
},
{
"brand": "_global_",
"scope": "ui",
"key": "enable_splh_weekly_by_channel",
"value": "true"
},
{
"brand": "_global_",
"scope": "ui",
"key": "enable_splh_weekly_by_day",
"value": "true"
},
{
"brand": "_global_",
"scope": "ui",
"key": "enable_splh_weekly_themes",
"value": "true"
},
{
"brand": "_global_",
"scope": "ui",
"key": "ins_rec_limit",
"value": "3"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__sos__id",
"value": "sos"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__sos__name",
"value": "Speed of Service"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__sos__threshold__weekly_warning",
"value": "300"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__sos__threshold__weekly_alert",
"value": "360"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__sos__threshold__weekly_units",
"value": "sec"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__sos__threshold__daily_warning",
"value": "5"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__sos__threshold__daily_alert",
"value": "20"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__sos__threshold__daily_units",
"value": "sec"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__sos__summary__sos__key",
"value": "sos"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__sos__summary__sos__name",
"value": "Speed of Service"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__sos__summary__sos__description",
"value": "Speed of service (SOS) measures how long an order takes to be completed"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__sos__summary__sos__units",
"value": "sec"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__sos__summary__sos__warning",
"value": "0.05"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__sos__summary__sos__alert",
"value": "0.2"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__sos__summary__sos__aggregation_type",
"value": "average"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__sos__metrics__sos__key",
"value": "sos"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__sos__metrics__sos__name",
"value": "Speed of Service"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__sos__metrics__sos__description",
"value": "Speed of service (SOS) measures how long an order takes to be completed"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__sos__metrics__sos__units",
"value": "sec"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__sos__metrics__sos__warning",
"value": "0.05"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__sos__metrics__sos__alert",
"value": "0.2"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__sos__metrics__sos__aggregation_type",
"value": "average"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__id",
"value": "splh"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__name",
"value": "Sales & Labor"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__threshold__weekly_units",
"value": "$"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__threshold__daily_warning",
"value": "5"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__threshold__daily_alert",
"value": "20"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__threshold__daily_units",
"value": "$"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__summary__splh__key",
"value": "splh"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__summary__splh__name",
"value": "Sales Per Labor Hour"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__summary__splh__description",
"value": "Sales Per Labor Hour measures the amount of sales generated per labor hour"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__summary__splh__units",
"value": "$"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__summary__splh__warning",
"value": "-0.05"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__summary__splh__alert",
"value": "-0.1"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__summary__splh__aggregation_type",
"value": "average"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__summary__wage_vs_sale__key",
"value": "wage_vs_sale"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__summary__wage_vs_sale__name",
"value": "Labor Cost Percentage"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__summary__wage_vs_sale__description",
"value": "Labor Cost Percentage (LCP) measures how long an order takes to be completed"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__summary__wage_vs_sale__units",
"value": "%"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__summary__wage_vs_sale__warning",
"value": "0.01"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__summary__wage_vs_sale__alert",
"value": "0.02"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__summary__wage_vs_sale__aggregation_type",
"value": "average"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__splh__key",
"value": "splh"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__splh__name",
"value": "Sales Per Labor Hour"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__splh__description",
"value": "Sales Per Labor Hour measures the amount of sales generated per labor hour"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__splh__units",
"value": "$"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__splh__warning",
"value": "-0.05"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__splh__alert",
"value": "-0.1"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__splh__aggregation_type",
"value": "average"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__splh__dimensions__sales__key",
"value": "sales"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__splh__dimensions__sales__name",
"value": "Sales"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__splh__dimensions__sales__weekly_units",
"value": "$"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__splh__dimensions__hours__key",
"value": "hours"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__splh__dimensions__hours__name",
"value": "Labor"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__splh__dimensions__hours__weekly_units",
"value": "hr"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__splh__dimensions__hours__invert",
"value": "1"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__splh__dimensions__wage_vs_sale__key",
"value": "wage_vs_sale"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__splh__dimensions__wage_vs_sale__name",
"value": "LCP"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__splh__dimensions__wage_vs_sale__weekly_units",
"value": "%"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__splh__dimensions__wage_vs_sale__invert",
"value": "1"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__splh__dimensions__employees__key",
"value": "employees"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__splh__dimensions__employees__name",
"value": "Employees"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__splh__dimensions__employees__invert",
"value": "1"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__lhvb__key",
"value": "lhvb"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__lhvb__name",
"value": "Labor Hours vs Schedule"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__lhvb__description",
"value": "Labor Hours vs Schedule measures the labor hours scheduled compared to budgeted hours"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__lhvb__units",
"value": "hr"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__lhvb__warning",
"value": "0.05"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__lhvb__alert",
"value": "0.1"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__lhvb__aggregation_type",
"value": "average"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__lhvb__is_summary",
"value": "false"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__svf__key",
"value": "svf"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__svf__name",
"value": "Sales vs Forecast"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__svf__description",
"value": "Sales vs Forecast measures the amount of sales compared to forecasted sales"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__svf__units",
"value": "$"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__svf__warning",
"value": "-0.05"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__svf__alert",
"value": "-0.1"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__svf__aggregation_type",
"value": "average"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__svf__is_summary",
"value": "false"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__wage_vs_sale__key",
"value": "wage_vs_sale"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__wage_vs_sale__name",
"value": "Labor Cost Percentage"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__wage_vs_sale__description",
"value": "Labor Cost Percentage (LCP) measures how long an order takes to be completed"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__wage_vs_sale__units",
"value": "%"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__wage_vs_sale__warning",
"value": "0.05"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__wage_vs_sale__alert",
"value": "0.1"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__metrics__wage_vs_sale__aggregation_type",
"value": "average"
},
{
"brand": "_global_",
"scope": "ingest",
"key": "channel_map_id",
"value": "1"
},
{
"brand": "_global_",
"scope": "ingest",
"key": "span_type_map_id",
"value": "1"
},
{
"brand": "_global_",
"scope": "ingest",
"key": "sales_snapshots_interval",
"value": "300"
},
{
"brand": "4182473",
"account": "246155785",
"site": "3899976",
"scope": "api",
"key": "kpi__splh__threshold__weekly_baseline",
"value": "77"
},
{
"brand": "4182473",
"account": "246155785",
"site": "3899976",
"scope": "api",
"key": "kpi__sos__threshold__weekly_baseline",
"value": "384"
},
{
"brand": "_global_",
"scope": "api",
"key": "weekly_time_series_max_weeks",
"value": "12"
},
{
"brand": "4182473",
"account": "246155785",
"site": "3899976",
"scope": "ds",
"key": "start_time_for_daily_aar",
"value": "13:00"
},
{
"brand": "4182473",
"account": "246155785",
"site": "3899976",
"scope": "api",
"key": "min_date",
"value": "2025-05-01"
},
{
"brand": "_global_",
"scope": "api",
"key": "sos_daily_unit",
"value": "sec"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__threshold__weekly_warning",
"value": "88"
},
{
"brand": "_global_",
"scope": "api",
"key": "kpi__splh__threshold__weekly_alert",
"value": "50"
},
{
"brand": "_global_",
"scope": "test",
"key": "last_updated",
"value": "2025-07-07"
}
]